## 1. Product Overview
Item | Description
Product Name | CYRIX AI
Product Vision/ Purpose | To empower individuals with real-time, intelligent health insights directly from their wrist, enabling proactive and personalized well-being management.
Business Goals / Key Success factors | Increase user acquisition and build a strong user base, Develop a sustainable monetization model (freemium/subscription), Improve product accuracy using data-driven insights
Primary Stakeholders | REVA UNIVERSITY

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
| Major features | Mandatory | Mandatory |  |  | (optional) | Mandatory | Mandatory | Mandatory | Mandatory
E1 | User Authentication | US1 | As a user, I want to sign up with email and OTP so that I can access my account securely. | Registration screen details | Must Have | 8 | To Do | Backend Dev team names | Can be a link to document | names
Pop Ups once registered
Login screen
OTP Generation
Sending OTP
Login Error Screen
US2
US7
E2 | Dashboard | US5 | As a user, I want to view analytics on a dashboard so that I can see trends quickly. |  | Should Have | 13 | In Progress | Frontend Dev
|  | US6 |  |  | Could Have
US3
Notes: | MoSCoW
|  | Must Have | Critical requirements that are essential for the project's success and must be delivered.
|  | Should Have | Important requirements that are highly desirable but not vital; the project can still be delivered without them, but it would be less ideal.
|  | Could Have | "Nice-to-have" requirements that are less important and have a lower impact if they are not included.
|  | Won't Have | Requirements that are not being delivered in the current project or timeframe, but may be considered for future iterations.
Story Points
|  | Fibonacci | 0,1,1,2,3,5,8,13,21,34,….
|  | (Modified) | 0,1,1,2,3,5,8,13,20 (points decided based on a User Story's complexity, effort needed & riks)
Ends at 20. Rarely extended to 40 and 100 for very large tasks.

## 3. Roadmap
Release |  | Key Features | Dependencies | Demo Status
Llist Epic Names
v0.1 | 2026-04-15 | Authentication, Dashboard MVP | None | On Track
v0.2 | 2026-04-17 | Analytics export, payment System | Requires API upgrade | Planned
v0.3 | 2025-04-18 | Wear os application | kotlin | Planned
v0.4 | 2025-12-06 | ML integration | python libs and dataset | Planned
v0.5 | 2025-12-13 | Wear os application - website API |  | Yet to Plan

## 4. Retrospective
Note: This is for the team to learn and improve. I have taught you in the class on Nov 4, 2025.
Ideally, the team should do this at the end of every release. How often you do , I leave it to you.
What Went Well | What Didn’t Go Well | Improvements / Action Items | Owner
Net time what will you do differently
Team collaboration was great | Test coverage was low | Automate test pipeline in next sprint | Test Lead